## Sheet1
Page Name | Time(Approx) | Constraints | Comments
Research page | 2 days | none
Publication Main | 2 days | none | 30% of the design was already made
Sign-up page | 1 day | none
Report inside + article insidepage | 2 days | none
Login page | 1 day | none | keep me signed in function(ajdusted)
Directors page | 2 days | backend
social bar | 1 day | none | Previously done ( we had to redesign and rewrite the code for the press the link button function)
report | 1 day | none
ongoing projects | 1 day | none | the social bar is removed ( should be only visibile when a specific event or article is present not many)
fund raising | 1 days | none
Career main | 2 days | none
Overview | 2 days | none
Opportunities | 1 days | none | the social bar is removed ( the strip in the bottom has its functions)
Fellow ship | 1 day | none
article | 1 day | none
fixing issues and comments | 1 day | none